Project Planning Phase

Project Planning (Product Backlog, Sprint Planning & Burndown)

| Date | 03 October 2026 |
| --- | --- |
| Developer / Student | Vinay Krishna A K |
| Project Name | Automated Network Request Management in ServiceNow |

1. Product Backlog, Sprint Schedule & Story Estimation

The product backlog is mapped directly to the implementation artifacts: the Service Portal (/sp) form variables, custom table u_database_table, and the 10-step Flow Designer workflow.

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Implementation Task | Story Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Service Catalog Intake | USN-01 | Create 'Network Request' catalog item under 'Network request Management' with Requested For and Opened on behalf of variables. | 2 | High |
| Sprint-1 | Contact & Variable Config | USN-02 | Configure form fields: User Name, Phone Number, Email ID, Mobile Number, and delivery Address with mandatory rules. | 2 | High |
| Sprint-1 | Connection & Billing UI | USN-03 | Build Type of Connection (New/Existing) and Mode of Payment (UPI/Card) choices with Total Amount calculation. | 3 | High |
| Sprint-1 | Database Persistence | USN-04 | Create custom table Database Tables (u_database_table) with Auto-Numbering prefix and matching column schema. | 3 | High |
| Sprint-2 | Workflow Initialization | USN-05 | Configure Flow Designer trigger (Service Catalog) and Step 1: Get Catalog Variables from Network Request item. | 2 | High |
| Sprint-2 | Record Creation Action | USN-06 | Configure Step 2: Create Record in Database Tables (u_database_table) mapping all ingested catalog variables. | 3 | High |
| Sprint-2 | Submission Acknowledgment | USN-07 | Configure Step 3: Send Email to requester confirming receipt with auto-numbered request tracking ID. | 2 | High |
| Sprint-2 | Approval Gate Configuration | USN-08 | Configure Step 4: Ask For Approval on Database Tables record, routing to designated Manager / Admin. | 4 | High |
| Sprint-3 | Conditional Logic Branching | USN-09 | Configure Step 5 If Condition evaluating approval state (True for Approved, False for Rejected). | 2 | High |
| Sprint-3 | Approved Branch Execution | USN-10 | Configure Step 6 Update Database Tables Record (Status: Approved) and Step 7 Send Approval Email to user. | 2 | High |
| Sprint-3 | Rejected Branch Execution | USN-11 | Configure Step 9 Update Database Tables Record (Status: Rejected) and Step 10 Send Rejection Email to user. | 2 | High |
| Sprint-3 | UAT & ACL Validation | USN-12 | Execute end-to-end UAT test passes, verify Flow Execution Details checkmarks, and validate platform ACLs. | 3 | Medium |

2. Project Tracker, Sprint Metrics & Velocity

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Actual Release Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 6 Days | 07 Sep 2026 | 12 Sep 2026 | 10 | 12 Sep 2026 |
| Sprint-2 | 11 | 6 Days | 14 Sep 2026 | 19 Sep 2026 | 11 | 19 Sep 2026 |
| Sprint-3 | 9 | 6 Days | 21 Sep 2026 | 26 Sep 2026 | 9 | 26 Sep 2026 |
| Total | 30 | 18 Days | 07 Sep 2026 | 26 Sep 2026 | 30 | 03 Oct 2026 (Final Sign-off) |

Velocity & Throughput Calculation:
• Total Story Points Delivered: 30 Points across 3 Sprints.
• Sprint Duration: 6 working days per sprint (Total Duration: 18 working days).
• Team Velocity per Sprint (Average): Velocity = (Total Points / Number of Sprints) = 30 / 3 = 10.0 Story Points / Sprint.
• Average Velocity (AV) per Iteration Unit (Story Points per Day): AV = Total Story Points / Total Days = 30 / 18 = 1.67 Story Points / Day.

3. Sprint Burndown Chart & Progress Analysis

Burndown Analysis: The burndown chart tracks the remaining effort from the initial 30 story points down to 0 at sprint completion. Sprint-1 burned down from 30 to 20 story points upon successful configuration of the Service Portal form and custom table schema. Sprint-2 burned down from 20 to 9 story points as the Flow Designer trigger, variable extraction, record creation, and approval actions were verified. Sprint-3 closed the remaining 9 story points by implementing the True/False conditional outcome branches, notification emails, and passing UAT execution.